OPERATIONS · PORT OF SOHAR · INTERNAL

# Aluminium Calls — Manpower Utilisation

The same four calls, read as manpower instead of hours. Lost time on a gang is lost time for everyone standing in it.

| Scope | Observed | Crew per shift | Period |
| --- | --- | --- | --- |
| 4 vessels | 123 shifts | 34.9 | Apr–Jul 2026 |

## 1. What the calls cost in manpower

| Man-hours assigned | Man-hours lost | Per man, per shift | Of all manpower |
| --- | --- | --- | --- |
| 30,082 | 5,299 | 1.2 h | 17.6% |

Read the third figure first. On average every man on board stood idle for 1.2 hours of a 7-hour shift — roughly a fifth of his working time. On MV Happy Founder it was nearly two hours per man, per shift.

Added together that is 5,299 man-hours, or what 757 full shifts would cost. That total is an accounting unit, not an event: nobody stood idle for a whole shift. The loss is spread thinly across 123 shifts and some 4,300 shift assignments. It is the same loss the time review reports as 290 hours, counted in people rather than in gang time.

## 2. Per vessel

| Vessel | Shifts | Crew / shift | Man-hours | Time lost | Man-hours lost | Per man, per shift |
| --- | --- | --- | --- | --- | --- | --- |
| MV Lady Sacha | 27 | 38.5 | 7,284 | 11.1% | 811 | 0.8 h |
| MV Walrus | 30 | 34.4 | 7,223 | 13.1% | 948 | 0.9 h |
| MV True Faith | 33 | 34.4 | 7,952 | 19.8% | 1,574 | 1.4 h |
| MV Happy Founder | 33 | 33.0 | 7,623 | 25.8% | 1,965 | 1.8 h |
| Total | 123 | 34.9 | 30,082 | 17.6% | 5,299 | 1.2 h |

The pattern follows the time review: the call that lost the most hours also kept the most people waiting.

## 3. How this is calculated

|  | Step | Source |
| --- | --- | --- |
| 1 | Count the crew on the vessel — every person listed against that vessel in the daily plan, excluding the separate “Store / Shifting” section. Averaged over the call, this gives the crew per shift used throughout this report. | Daily planning sheets |
| 2 | Multiply by 7 hours and by the number of shifts worked — an 8-hour shift less one hour of break; three shifts cover the day. | Productivity reports |
| 3 | Apply the share of time lost for that vessel to those man-hours. | Productivity reports |

## 4. What this figure is, and what it is not

It is an upper bound, not a measurement. The calculation assumes that when the gang stands still, the crew assigned to that vessel stands still with it. For the men on the hook — crane driver, signalman, hold dockers — that holds. A forklift on the quay may well carry on with something else. Read the figure as up to 5,299 man-hours — and read the per-man figure as an average across the whole crew, not as a queue of idle men.

- Every shift is counted as 7 hours. A fifth of the shifts ran 12 hours as overtime. Counting those at 7 hours as well keeps the arithmetic simple and understates the total by roughly 11%. The real figure is higher, not lower.

- These are plans, not attendance. The daily plan records who was rostered, not who turned up. Replacements and reassignments are not reflected.

- Own and hired labour are counted the same. Roughly a third of the crew comes from contractors. For a cost figure they would need separating; for a manpower figure they do not.

## 5. Why not FTE

An FTE is a full-time position over a year. These four calls span three months, so expressing the loss as a fraction of an FTE invites the wrong conclusion — that two or three people are permanently idle. They are not. The loss is concentrated in specific shifts on specific calls.

757 shifts says the same thing without that risk, and it is a unit the operation already works in. Should an FTE figure be required for budgeting, it needs the annual hours Steinweg applies per position; that number is not assumed here.

## 6. Where this goes next

The weakness above — that we assume who stood still rather than observe it — is being closed. The gang time observation study now running records, every five minutes, whether each individual position is working or standing still. Once twenty shifts are in, this conversion can be replaced by a measured ratio: not how many people were assigned, but how many were actually idle. The daily plans remain the other half of that picture: they supply the denominator, which the observation study does not capture alone.

Sources: daily planning sheets and the productivity reports per vessel, 16 April – 13 July 2026. Companion document: Aluminium Export — Time Utilisation Review (OPS-RPT-ALU-01), which reports the same loss as gang hours.

OPS-RPT-ALU-02 · Rev 1.1 · Internal