OPERATIONS · PORT OF SOHAR · BERTH B-6

# Aluminium Export — Time Utilisation Review

Four vessel calls, April to July 2026. Where the working hours went, recorded shift by shift.

| Scope | Observed | Period |
| --- | --- | --- |
| 4 vessels | 117 shifts | Apr–Jul 2026 |

## 1. What the period delivered

| Shift hours | Hours worked | Net utilisation | Hours lost |
| --- | --- | --- | --- |
| 1,549.6 | 1,268.1 | 81.8% | 281.5 |

Across the four calls the gangs were productive for 81.8% of the hours booked. The remaining 281.5 hours is the subject of this review, set out exactly as recorded shift by shift in the operational reports both parties receive.

## 2. How the hours divide

|  | Hours | Share |
| --- | --- | --- |
| Worked | 1,268.1 | 81.8% |
| Lost — terminal side | 131.0 | 8.5% |
| Lost — vessel side | 150.6 | 9.7% |
| Total shift hours | 1,549.6 | 100% |

| Vessel | Ops start | Shifts | Shift h | Worked h | Lost h | Terminal | Vessel |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MV Lady Sacha | 16 Apr | 27 | 355.5 | 315.9 | 39.6 | 29.3 | 10.3 |
| MV Walrus | 10 May | 30 | 391.0 | 339.6 | 51.3 | 35.3 | 16.0 |
| MV True Faith | 6 Jun | 33 | 446.2 | 357.8 | 88.3 | 36.6 | 51.8 |
| MV Happy Founder | 2 Jul | 27 | 357.0 | 254.7 | 102.3 | 29.8 | 72.5 |
| Total | — | 117 | 1,549.6 | 1,268.1 | 281.5 | 131.0 | 150.6 |

Hours are rounded to one decimal place; individual figures may therefore not sum exactly to the totals shown.

Two observations from the table above. First, the terminal’s own share has been stable across all four calls — between 29.3 and 36.6 hours. Second, the vessel-side share has not: it moved from 10.3 hours on the first call to 72.5 on the fourth. The growth in total lost time comes almost entirely from that second column.

## 3. What the lost hours were

Every hour below is booked against a reason code in the shift report. Nothing is estimated and nothing is moved between the two columns.

| Vessel side | Hours |
| --- | --- |
| Idle — waiting on (un)lashing | 83.3 |
| Vessel idle (other) | 59.4 |
| Vessel crane breakdown | 7.8 |
| Subtotal | 150.6 |

| Terminal side | Hours |
| --- | --- |
| Other operational delay | 90.9 |
| Late start / early finish | 38.2 |
| Crane breakdown & waiting for cargo | 2.0 |
| Subtotal | 131.0 |

## 4. The single largest item

Read by reason rather than by side, one item is larger than any other: chocking, lashing and securing. It appears in the lashing column on two vessels and inside the general vessel-idle column on the other two, where the shift notes name it explicitly. Added together across all four calls it accounts for 112.4 hours — 40% of all time lost, and 75% of vessel-side time.

| Vessel | Hours on chocking, lashing and securing |
| --- | --- |
| MV Lady Sacha | 11.8 |
| MV Walrus | 13.1 |
| MV True Faith | 16.2 |
| MV Happy Founder | 71.3 |

Across the four calls the figure ranged from 11.8 to 71.3 hours. The call with the highest figure is also the call that lost the most time overall.

Source: the shift reports issued during each call for MV Lady Sacha, MV Walrus, MV True Faith and MV Happy Founder. Hours are as booked in those reports. This review covers time utilisation only.

OPS-RPT-ALU-01 · Rev 1.0